Soapbox Derby Planning Doc Roles and Considerations Checklist

- Directors

  - Race Director

  - Town Liaison (Fire, Police, Selectboard, etc)

  - Financial (income, expenses, insurance, etc)

  - Publicity / Website / Social Media (Schedule / Documentation)

  - Sponsors / Underwriters / Other Partners

  - Racers Liaison

  - Vendors / Raffle

  - Supplies (hay bales, caution tape, timers, etc)

  - Video / Photography

- Volunteers

  - Check-In Station / Cart Inspectors

  - ATV / Cart Transport to race track, and to starting line after each heat

  - Starting Line / Cart Wranglers

  - Finish Line Timers

  - Finish Line Cart Wranglers

  - Announcers / Judges

  - Results Tabulator

  - Crowd Control

- Race Day Issues to Consider

  - Parking

  - Race Day Schedule

  - Vendors Area (Beer Garden?)

  - Spectators Areas

  - First Aid Tent

  - Bathrooms

  - Track Detail, Hay Bale and Barriers Placement

  - Traffic Signage (keep cars away from race area)

  - Public Address (PA) System

  - Trophy Ceremony (buy trophies)

  - Police

- Documentation Needed for Racers

Areas Associated with the Race

- Cart Specs and Requirements

- Racer parking (they will all have trailers)

- Cart check-in station

- Race starting line

- Race track

- Spectator area / bathrooms

- Announcers platform / tent

- Race end stretch and finish line

- Racer staging for return up hill

- Vendors area

Event Specific Materials

- Hay bales!

- Coffee and pastries for set up in the morning

- Garden gloves to handle the bales. Each bale weighs about 60 lbs!

  - CONTACT THE JAIL FOR ORANGE SUIT ASSISTANCE WITH HAY

- Leaf blower to sweep hay off track before race, and after bales are returned to truck

- Barricades (hiway dept loan)

- Race car scales for weighing / inspection

- Measuring tape for inspection

- 20’ Trailer flatbed for announcers? Portable stage?

- Public Address system

- Gas generator for announcers PA and several extension cords, and spare gas tank

- Port-O-Potties

- 2 Cart start-blocker

- Caution tape and tomato stakes for spectator area and race track

- Two-way radios for race officials

- Chalking machine for vendor slot marking, and start and finish lines

- Folding tables and chairs for announcers and first aid tent

- Tent and table and chairs for race merchandise booth, cash box, etc.

- “Event boxes” cardboard garbage / recycling cans (DPW / FCSW)

- Sheets of paper, cut into ovals, and sharpies for on-day racer registrant cart numbers

- Scotch and masking tape and staple guns, clipboards, pens and markers

- Blank entry forms (if you’re allowing same-day registration)

- Medical supply bag

- 50-50% Raffle tickets

- Lengths of strong rope and carabineers for pulling carts

Merchandise and Trophies

- T-Shirts

- Previous years stadium cups and pint glasses

- Posters

- Trophies

  - 9 total: 3 for each age group

  - Additional trophies for style (created by local artists)

- Table

- Chairs

- Tent

- Cashbox

- Price Signs

Signage

- Paper signs affixed to blank lawn signs, each stapled to poles, and placed in strategic spots around town for traffic control

- Traffic Control plan

- 10’ banner attached to the announcers platform

- Hay Bale advertising signs

- Cable ties to affix bale signs to bales